## Sheet1
|  | Requirements Gathering | [8 empty] | Design |  |  | Construction | [9 empty] | Testing |  |  | Review
|  | use case and ER diag | use case and ER diag | use case and ER diag | DFD | DFD | DFD | Sequence Diagram and State Diagram | Sequence Diagram andState Diagram | Sequence Diagram/State Diagram | Login/ dashboard of Faculty and Student/ Edit Profile | Student and Faculty Course/Assignment/enroll student list | Student and faculty Grades/Resources | Login/ dashboard of Faculty and Student/ Edit Profile | Login/ dashboard of Faculty and Student/ Edit Profile | Student Course/Assignment | Student Course/Assignment | Faculty Course/Assignment | Faculty Course/Assignment | Student Grades/Resources | Student Grades/Resources | Faculty Grades/Resources | Faculty Grades/Resources | Testing-1 | Testing-2 | Testing-3 | Documentation review | End of the project
Person | Question | Meeting 1 | Meeting 2 | Meeting 3 | Meeting 4 | Meeting 5 | Meeting 6 | Meeting 7 | Meeting 8 | Meeting 9 | Meeting 10 | Meeting 11 | Meeting 12 | Meeting 13 | Meeting 14 | Meeting 15 | Meeting 16 | Meeting 17 | Meeting 18 | Meeting 19 | Meeting 20 | Meeting 21 | Meeting 22 | Meeting 23 | Meeting 24 | Meeting 25 | Meeting 26 | Meeting 27
|  | 18th February | 2nd March | 4th March | 6th March | 8th March | 9th March | 11th March | 13th March | 16th March | 19th March | 22nd March | 25th March | 26th March | 28th March | 31st March | 2nd April | 5th April | 7th April | 10th April | 12th April | 15th April | 17th April | 18th April | 20th April | 4th May | 5th may | 7th May
Harvish | What did you do yesterday? | Use case - Identify Actors | Use case - Identify use case for individual actor | Use case - Making Rough use case diagram | DFD - started with level 0 | Finished with level 0 DFD | Started with level 1 dfd | Identified different states of state diagram | Identified different events | Finalise the states and flow of diagram | Identified the layout of the Edit profile screen | Designed the edit profile page on Adobe XD | Designed the page where students can see the list of assignments | Build the page for resources on faculty end | Developed edit profile page | Rebuilt the profile page as there was not much content in it | Coded backend for the student assignment list | Check the previously built pages and their connections because of issues | Started working on assignment creation page for Faculty users | Finished the assignment page for Faculties | Started working on the resources page for students | Finished the student resources page | Started working on assignment list for Faculty side (backend and frontend) | Finished assignment list for Faculty side | Learnt how to work on Django Tests | Had previously started working on tests before endsems | Review all documents once for approval and verification perpose | Project completed successfully
| What will you work on today? | Use case - Identify use case for all individual actors | Use case - Making Rough use case diagram | DFD - started with level 0 | DFD - level 0 | Build level 1 DFD | Level 1 DFD progress | Identified different events | Finalise the states and flow of diagram | Draw the state diagram | Designed the edit profile page on Adobe XD | Designed the page where students can see the list of assignments | Designed the page for resources on faculty end | Developed edit profile page | Rebuilt the profile page as there was not much content in it | Coded backend for the student assignment list | Connect backend and frontend of Assignment list for Students | Started working on assignment creation page for Faculty users | Finished the assignment page for Faculties | Started working on the resources page for students | Finished the student resources page | Started working on assignment list for Faculty side (backend and frontend) | Finished the task | Learn how to work on Django Tests | Start building the tests.py | Revise unit testing and build them for project | Give suggestions and modifications to team members for document
| Do you have any obstacles? | some problems on identifying actors | Use case - can backgroud process be a part of the use case | No | DFD - building the simple structure of dfd | Identifying the processes | How to select connections and databases | No such obstacles faced | No such obstacles faced | Selecting the proper tool for State diagram | No | No | No | No | Decide what else can be added to the profile page | Django URLS were done differently, understanding that | Understanding the URLS | No | No | Lack of CSS experience | CSS | No | Connecting backend and frontend | Had to learn how to implement Tests from scratch | Had to learn how to implement Tests from scratch | No obstacles | No obstacles
Devam | What did you do yesterday? | Identify the enities of the application | Searching tools for use case | Connecting the entities | Identified all the actors and made a rough DFD | Completed DFD level-0 | Drawed a rough skecth of the diagrams with actors and processes | Decided the states of the system | Found all the states and events | Finalized the flow of the diagram | Discussed the functionalities of edit profile | Completed the design of edit profile | Completed the design of the list of resources | Completed the design of faculty resources | Completed edit profile, but has bugs | Finalized the coding of edit profile | Completed the coding for student assignment page | Finalized the student assignment page and its functionality | Completed the coding for faculty assignment page | Finalized the faculty assignment page and its functionality | Completed the backend coding | Finalized the student resources page and its functionality | Completed the front-end of faculty grades page | Completed the construction | Gained knowledge about framework testing | Started url testing at student-end | Completed the testing part. | Project completed successfully
| What will you work on today? | Searching tools for use case | what are the attributes if the entities of the entities | Generalizing the use case | DFD - Made a simple level 0 | Decided the number of process in the diagram | Identifying the connection between process and databases | Finding click events for state change | Deciding the flow of the state diagram | Draw the state diagram | Start designing the edit profile screen on adobe XD | Designed the frontend of how the list will be displayed on adobe XD | Design the page for resources on the faculty side on adobe XD | Started pair-coding (in pairs of 2) of the edit profle page | Rebuilt the page and add extra contents to fill the page | Coded the front-end for student assignment page | Connect the backend and the front-end for the page | Coded the front-end for faculty assignment page | Connect the backend and the front-end for the page | Coded the back-end for student resources page | Connecting the front-end and back-end of the student resources page | Start the front-end coding for faculty grades | Remove bugs of alignment of the page | Learning about framework testing | Start url testing at student end | Complete the remaining part of the student test module | Review all the documents and diagrams
| Do you have any obstacles? | identifying weak and strong entities | to find which tool is proper for use case | Finalizing the Use case | Writing about the data flowing in every connection |  | How to do inter-process connection | No obstacles faced | No obstacles faced | Connecting the self-states | No obstacles found | No obstacles found |  | Fill the page as it had limited functionalities | No obstacles found | Alignment of the characters | Removing the bugs for data fetching | No obstacles found | Alignment of the objects on page | Bugs regarding fetching of the resources | No Obstacles found | Alignment of the objects of the page | No obstacles found | No obstacles found | coding from scratch | No obstacles found | No obstacles
Nancy | What did you do yesterday? | Identify the relationships between entities | Identifying bridge entities | Took feedback from others and made required changes | Refered to different diagrams for understanding rules of DFD | Started with entities and process | Completed level-1 and started level-2 | Literature and rading rules about sequence diagram | worked on sequence diagram of admin | worked on sequence diagram of faculty | Identified the layout of the student dashboard | Designed student dashboard screen on tool | Designed Enrolled student list screen in adobe | Completed Screen designing and kick start coding by making models | Made models and started constructing student dashboard backend | Done with student dashoard backend | Frontend coding of student assignment module | Done with student assignmnet frontend | Frontend coding of faculty assignment module | Done with faculty assignmnet frontend | Stared backend of student resources | Completed backend of student resources | Started backend of faculty grades | Done with construction | Started url testinf of faculty side | Started url testinf of student side | Completed the testing of URL. | Project completed successfully
| What will you work on today? | Identifying bridge entities | Formation of complete ER diagram | Formation of complete ER diagram and Group discussion | Started identifuying process and entity | Added database and decided the flow and completed level 1. Stared Level-2 for student and faculty grades and resources | Done with level-2 DFD | Identify actors, lifelines connections and started working on sequence diagram of admin | start working on sequence diagram of faculty | stat rworking on sequence diagram of student | Design student dashboard screen in tool | Designing Enrolled student list screen in adobe tool | Design screen of resource page on student side in adobe | backend construction of student Dashboard | Solved errors in redirecting and passing parametres | To start frontend of student assignment module | Solving problem in CC and aligning everything properly | To start frontend of faculty assignment module | Solving problem in CC and aligning everything properly | To start backend of student resurces | To complete backend of student resources | To start backend of faculty grades. | To solve delete grades problem in backend | To start URL testing of all modules on faculty side | To solve faculty grades URL error and start with url testing of student modules | To complete url testing of student modules | Give suggestions and modifications to team members for document
| Do you have any obstacles? | At times relationships fromed loops that were to be resolved | No obstacles for now | No obstacles | Facing confusion about data flow | No obstacles | No obstacles | None | None | No obstacle | selecting layout | No obstacle | None | Facing errors in redirecting and passing parametres | No obstacles | Faced problem in CSS | None | Faced problem in CSS | None | None | None | Difficulty in implementing Delete grades option | None | Faculty grades URL was having some error | None | None | No obstacles
Hardi | What did you do yesterday? | Use case - Define the Scenario | Use case - Incoorporated include functionality within use cases | Use case - Finalizing remianing thing | Identified faculty processes of level 1 and relationship with faculty entity | Made Level 1 DFD | Level 2 of user processes | Identify actors, lifelines connections | worked on sequence diagram of admin | worked on sequence diagram of faculty | Identified the layout of the student dashboard | Design student dashboard screen in adobe | Design Enrolled student list screen in adobe | Decide color theme of student dashboard | Start designing student dashboard and also navigation sidebar | Decide input fields | Started frontend design of Student upload form | Decide input fields | Started frontend design of Faculty add assignment form | Decide layout and functionalities | Started frontend design of student resources page | Decide form layout and input fields | Started frontend design of faculty grades upload form | Find a few test plan document for reference | Finalize what points should be included in test plan document by refering the test plan documents found for reference | Finalize all manual testing to be done on student side | Review all documents once for approval and verification perpose | Project completed successfully
| What will you work on today? | Use case - Incoorporated include functionality within use cases | Use case - Finalizing remianing thing | Use Case- Draw diagram in the online tool | Making level 1 DFD | Level 2 user process - faculty assignments, student assignments | Level 2 organizer process - add,modify,delete events | worked on sequence diagram of admin | worked on sequence diagram of faculty | worked on sequence diagram of student | Design student dashboard screen in adobe | Design Enrolled student list screen in adobe | Design screen of list of assignment to be graded on faculty side in adobe | Start frontend design of student dashboard and also navigation sidebar | Completed the frontend of student dashboard | Started frontend design of Student upload form | Completed frontend design of Student upload form | Started frontend design of Faculty add assignment form | Completed frontend design of Faculty add assignment form | Started frontend design of student resources page | Completed frontend design of student resources page | Started frontend design of faculty grades upload form | Completed frontend design of faculty grades upload form | Finalize what points should be included in test plan document by refering the test plan documents found for reference | Finalize all manual testing to be done on student side | Completed all the manual testing on student side | Give suggestions and modifications to team members for document
| Do you have any obstacles? | Taking care of each small requirement | identifying weak and strong entities | No such obstacles faced | organizing level 1 structure | No obstacle | Representing different views of different category of events in DFD | connections | Identifing alternatives | No obstacle | No obstacle | No obstacle | choosing layout | responsiveness of page | Aligning everything properly | Aligning everything properly | No obstacle | Aligning everything properly | No obstacle | Padding | No obstacle | Aligning input fields | No obstacle | It have been very tough to decide what factors define the test plan correctly | How many and which testings should be included | testing with each kind of entry | No obstacles
Foram | What did you do yesterday? | Figuring the stakeholders for the Lms | Entities for ERD | designed the daigrams | Go through different resources for DFD | Completed half of the level-2 | Finished level-2 | Gathered resources for state daigram | Got all the state and click events of the daigram | Finalized the daigram | Gathered different ideas for design | Completed the faculty dashboard | Completed the student upload assignment page | Finalised the layout for list of student grade page | Finalized all the three pages layout, structure and snyc. | Go through some tutorials for Django views | Decided views for student upload backend | Completed student upload assignment | Figured out the views for faculty upload assignment | Completed django views for faculty upload | Completed the designing of student grades | Figure out the faculty grade upload views | Completed the views and functions of faculty grade upload | Studied the testing models for django | Figured out the django testings | Figuredout the errors faced and the failed testcases | Reviewed all the documents, designs, daigrams and testing with the team | Project completed successfully
| What will you work on today? | actors, functionalities and relationships for use case | figuring out attributes, relationships and bridges. | Discussion with the team and finalizing the Daigrams | Constructing level-2 DFD diagram | Further construction of level-2 | Finalized level-2 daigrams | Decided the states of the daigram | Decided the flow | Implemented it | Designed the structure and colours of faculty dashboard | Designed the student upload assignment screen, the sequence and structure of the upload process on the student side | Design the list of students grade page on faculty side and how to present them. | Finalised the layout and sychronise them with the faculty dachboard | Completed the frontend of faculty dashboard | Started backend developmen for student upload assignments. | Implemented them along with uploading file views and connected it with frontend and database | Started backend for faculty upload as well | Making the connections with frontend and database | Designed the student grades list page with proper display and sync with the theme | Make connections with the backend | Design the django views for faculty grade upload | Make the connections and fetching the submissions to the faculty side | Watch tutorials and tried to implement it for the website | Write the tests for models with different test cases | Revise unit testing and implemented various test cases | Implemented the changes, and give out suggestions for the documents
| Do you have any obstacles? | considering the minute details | no obstacles | No obstacles | Confusion in distinguishing and adding data | No obstacles | No obstacle | confusion in understanding thouroughly | No obstacle | No obstacle | No obstacles faced | No obstacles faced | How to present the list on the page | No obstacles faced | responsiveness of page | Understanding the framework | Obstacle in uploading the file | Faced problem in handling errors | no obstacles | no obstacles | problems in backend connections | No obstacles | No obstacles | Understanding django tests | Faced problems in running the test | No obstacles | No obstacles
Dhatri | What did you do yesterday? | Studied basics of ER Diagram | Identify roles of stakeholders | Sketching rough ER diagram | Referred to various websites stating information and rules of DFD | Completed DFD level 1 and decided processes for level 2 | Arranging level 2 and finalising the diagram | Literature review and watching youtube videos on sequence diagram | admin sequence diagram complete | completed sequence diagram of faculty | finding some examples of screen designs | designed final dashbaord screen | Finalised the cards view and designed assignment list page for faculty | writing views in django to fetch the reuiqred details for faculty dashbaord | Finalising the code and solving some CSS errors of faculty dashboard page | Writing the django views for uploading assignment solution on student side | Integrating the validations required | Writing the django views for upload the assignment to students | Fixing the file upload issue | Writing django views to fetch the uploaded grades by faculty | Fixing the views as grades were not fetched | Writing the views to upload the resouces and view the uploaded views | Completing the screen designing | Reviewing the website | Writing django tests for models | implementing different test cases | Reviewing the digrams and documentation | Project completed successfully
| What will you work on today? | Identify roles of stakeholders | Sketching rough ER diagram | Finalising the Diagram and discussion with team members | Construction of DFD Level 1 | Started constructing level 2 | preparing different digrams for each process for simplicity | Admin sequence diagram | Figuring the structure of faculty sequence diagram and perparing conditional block for login | Working on sequence diagram of students and finalised the sequence diagram | designing faculty dashbaord and trying different color schemas. Also figured out the contents to be displayed on the dashboard | Designed assignment screen for fsculty. The uploaded assignments are visible on this scrren. | designed assignment evaluation page for faculty | coding the screend design | Rendering the information to dashboard page | Designing the form for input | Fixing the front end design | Designing the form for uploading the assignemnt. | Fixing the front end design | Writing code for screen designing | Finalising the grades view | Designing and writing code for resources section | Fetching the upload resource details on the screen from views | reivewing literatures to write test cases for models | testing models and deciding different test cases | Testing models | Discussing the changes required in documents
| Do you have any obstacles? | Defining relationships | Deciding attributes | May require more upgrade in ER diagram | confusion in the data to be flowed | Arrangment of level 2 | no obstacles | No | dilemma in database connection | No | No | confusion in presentation of the assignment list | No obstacles | No | CSS coding | No | No | Problem faced while choosing the file | No | No | No | No | No obstacles | Running the tests | No | No such obstacles | No
Dhir | What did you do yesterday? | Identify Actors for Use case | find tools for use case | rough use case diagram | Learned about different levels for DFD. | Finished few DFD diagrams. | Completed my share of work on Level 2 DFD diagrams | Learned about sequence diagram | Started working on the sequence diagram | finished sequence diagram of faculty | identify the layout for login screen | identifylayout of faculty course page | identify the layout for the students grade page | Identify the layout for the login page of both students and faculty | Identif the layout for the login page of faculies | Identify the layout for the Student course page | Designed the front end for student course page | Decided upon the faculty -view course page layout | Designed the front end for Faculty course page | Took some inspiration on how to design student grades from auris | Designed the student grade page | Learned about website architecture diagram from google and youtube videos | Learned about software architecture diagram from google and youtube videos | Watched youtube videos and google on manual testing | Wrote all the manual test description before writing test steps | Completed almost half of the manual testing | Completed manual testing | Project completed successfully
| What will you work on today? | Search for tools for Use case | searching on different entities | completion of use case in miro | Start with Level 2 DFD diagram. | To complete other Level 2 DFD diagrams | Reviewing all the level 2 DFD Diagrams | Understand sequence diagram with more detail | Work on sequence diagram of faculty | Reviewing and finalize the sequence diagram | designing login screen for students and faculty | Designed faculty course page where faculty can see his courses | Design the student's view grades in adobe xd | Design the login page of student | Design the login age of faculty | Design the front end of the students course page | Connect in the page in the flow of the project | Designed the faculty courses with synchronous to the student course page | Connected the page in the flow of the project | Designed the student view grades page | Connected the page in the flow of the project | Draw website diagram in miro | Draw software architecture diagram on draw io | Start with manual testing | To start the test step for each testing and to conclude whether its working or not | Finished writing all the test steps for all the manual testing | To review manual testing and apply any changes if neccesaary
| Do you have any obstacles? | problems in strong and weak entities | no obstacles faced | overcoming different opinions from team members | little confusion about which all data to add | No obstacles | No obstacles | unclarity on database connection | No obstacles | No | some functionalities of Abobe XD | No obstacles | No obstacles | No obstacles | No obstacles | No obstacles | Errors in connection faced | No obstacles | Errors faced in connection | No obstacles | Errors faced while connecting | No obstacles | Faced difficulties in service layer and data layer | difficulties in finnding all the tests and its descriptions | No obstacles | No onstacles | No obstacles
Prasham | What did you do yesterday? | Revised ER diagrams | Made a rough ER diagram | Presented the ER diagram to all group members | Identified the Level 2 DFD diagrams to be made | Completed all Level 2 Data Flow Diagrams | Consulted teamates for finalization of DFDs. | Understood a state diagram in detail by visiting different websites | Determined the events | Confirming the states, events and flow of the diagram with teammates | Identified the layout for Login Screen | Reviewed other similar websites to include the best possible features for the Student Course Page | Determined the features that can be included in the Faculty-Post Grades Page.(Add comments and enter marks in a fixed range | Developed a front end design of the Login Screen | Completed development of the Login page including back-end | Visited various resources for implementation of features decided for the Student-Course page | Completed back-end development of the Student-Course Page | Developed the front-end of the students enrolled page for Faculty members | Back-end development of the students enrolled page | Figured out how to implement the decided features | Completed back-end construction of Studentg grades page | Start backend development of Faculty upload resources | Implementation of file selection for faculty | Made small changes wherever required to complete construction of the website | Started performing tests and obtained results | Completed manual testing for Faculty pages | Review all documents once for approval and verification perpose | Project completed successfully
| What will you work on today? | Putting together all entities | Making the final ER diagram | Making changes according to the suggestions proposed | Initial Development of Level 2 Data Flow Diagrams | Review all the Level 2 diagrams again | Making required changes suggested by teammates | Determining the states | Finalizing the flow of the state diagram | Drawing the finalized state diagram | Designing the Login Screen in Adobe XD | Designing the Student Course Page in Adobe XD | Designing the Faculty-Post Grades page in Adobe XD | Approving the Design and styling with the teammates | Performing validation of the Login form | Starting back-end development of the Student-Course Page | Final connection of back-end and front-end of Student-Course Page | Work on obtaining required data for the students enrolled page | Connecting front-end and back-end pages | Start back-end construction of Student grades page | Connecting front-end and back-end pages | Continue development of the Upload Resources page | Completing final development of back-end design of the Upload resources page | Writing all possible test cases for manual testing on Faculty pages | Continue performing tests | Review the tests and testing documents | Give suggestions and modifications to team members for document
| Do you have any obstacles? | No obstacles faced | Defining relationships between 2 entities | Difference of opinion among team members | No obstacles | Connection of processes and data stores | No obstacles | Identifying states between initial and final states | No obstacles | No obstacles | Getting familiar with Adobe XD | No obstacles | No obstacles | Implementing required design with CSS | No obstacles | No obstacles | Faced various unknown errors in connection | No obstacles | No obstacles | No obstacles | No obstacles | Implementing file selection for Faculty | No obstacles | No obstacles | No obstacles | No obstacles | No obstacles